## Sheet1
Sprout Inc. Sprint 4 | Sprint Goal: The goal of this Sprint is to continue building and improving components needed for ProfileScreen, as well as getting started on MatchScreen.
User Story | Tasks | Story Type | Story Points | Team Member | Percentage
As a user, I would like the ability to change my user profile so that way it can be as up-to-date as possible. | Continue Seting up Database | NF | 4 | Taidgh & Matt | 35
| Improve Temporary Database in Frontend | F | 3 | Andrew | 10
| Continue creating bio card on profile | F | 3 | Noah | 15
| Prevent IceBreaker inputs to be empty | F | 3 | Enoch | 10
| Continue creating an edit Bio screen | F | 3 | Noah | 15
As a single person, I would like the ability to easily match with someone in order to start a relationship | Design basic outline for MatchScreen | NF | 3 | Kody | 15