## Sheet1
Sprout Inc. Sprint 5 | Sprint Goal: The major goal of this sprint is to finish up what we did not finish from Sprint 4. In addition, implement the outline of MatchScreen, which was designed in Sprint 4, and greatly improve the reusability of IceBreaker component.
User Story | Tasks | Story Type | Story Points | Team Member | Percentage
As a user, I would like the ability to change my user profile so that way it can be as up-to-date as possible. | Continue Seting up Database | NF | 4 | Taidgh & Matt | 25
| Finish improving Temporary Database in Frontend | F | 3 | Andrew | 10
| Finish creating bio card on profile | F | 3 | Noah | 10
| Update IceBreaker so it takes ice breaker questions and answers as props | F | 3 | Enoch | 10
| Continue creating an edit Bio screen | F | 3 | Noah | 10
As a single person, I would like the ability to easily match with someone in order to start a relationship | Implement MatchScreen outline | F | 3 | Kody | 15
| Display IceBreakers of other users' on MatchScreen | F | 3 | Enoch | 10
As a user, I would like the ability to register for an account in order to log into my account on different devices. | Store IceBreaker to each user | F | 3 | Enoch | 10