## Sheet1
Sprout Inc. | Sprout Dating Product Backlog
ID | Story | Sprint | Priority | Story Status | Story Points
20 | As a user, I would like the ability to register for an account in order to log into my account on different devices. | 1 | H | IP | 10
3 | As a user, I would like the ability to change my user profile so that way it can be as up-to-date as possible. | 2 | H | IP | 5
1 | As a single person, I would like the ability to easily match with someone in order to start a relationship | 3 | H | W | 10
5 | As a user, I would like to be able to talk and chat with people that I match with in order to get to know them better. | 4 | H | W | 8
6 | As a user, I would like to be able to send messages through the app so that I don’t have to give out contact information unless I want to. | 4 | H | W | 8
7 | As a user, I would like the ability to see a list of those that I have matched with to quickly message them. | 5 | H | W | 6
2 | As a user, I would like the ability to 'like' or 'dislike' someome by swiping or pressing a button in order to show my interest in someone. | 3 | H | W | 10
8 | As a user, I would like to see profile pictures of the person, AFTER we have matched with each other, in order to see who I matched with. | 4 | H | W | 5
9 | As a user, I would like the ability to go back and see profile pictures of people that I have matched with for extra talking points. | 6 | M | W | 5
4 | As a user, I would like the freedom to make my profile unique by changing text colors, profile colors, and text fonts, in order to make myself stand out. | 6 | M | W | 3
16 | As a user, I would like to have notifications when I match with someone or get a message so I can react quickly. | 6 | M | W | 2
13 | As a college student, I would like to specify the age range of people I’m looking for in order to only find people my age. | 6 | M | W | 2
10 | As a user, I would like to have the ability to block someone so they can’t message me anymore. | 6 | L | W | 1
11 | As a user, I would like to quickly report/block someone at the press of a button, if they break terms of service. | 6 | L | W | 1
12 | As a user, I would like to be able to report someone if they have a fake profile. | 6 | L | W | 1
14 | As a person who isn’t very creative, I would like to answer a given prompt in order to make a good first impression. | 6 | L | W | 3
15 | As someone with specific tastes I would like to be able to specify my likes and dislikes with values to show how much I like or dislike each item. | 6 | L | W | 10
17 | As a user, I would like a list of first date suggestions so I can offer them to my match. | 6 | L | W | 8
18 | As a user, I would like to specify types of dates that from a list of suggestions in order to pick one that is best for me. | 6 | L | W | 5
19 | As a user I would like to be reminded to take a break to limit my on-screen time throughout the day.” | 6 | L | W | 3